## Project Planner
A-Level Computer Science - Programming Project Planner
Student Name: [Enter Name] ¦ Target Deadline: Thursday 17 December 2026
Week | Dates (Mon - Sun) | A-Level Project Phase & Suggested Focus | Planned Weekly Objectives & Key Milestones | Actual Work Completed | Status | Teacher Feedback / Notes
Week 1 | 14 Sep - 20 Sep | Analysis | Define user requirements, write stakeholder description, establish clear project scope & limitations. |  | In Progress
Week 2 | 21 Sep - 27 Sep | Analysis | Create comprehensive hardware/software requirements & finalize measurable success criteria. |  | Not Started
Week 3 | 28 Sep - 04 Oct | Design | Design system architecture, data structures (databases/classes), & write high-level pseudocode/algorithms. |  | Not Started
Week 4 | 05 Oct - 11 Oct | Design | Wireframe user interfaces (UI), map out navigation flow, and construct an explicit Test Plan matrix. |  | In Progress
Week 5 | 12 Oct - 18 Oct | Developing (Prototypes) | Set up IDE, environment, version control. Code a basic prototype focusing on core database/API connectivity. |  | In Progress
Week 6 | 19 Oct - 25 Oct | Developing (Core Function) | Develop core backend logic & algorithmic operations. Document iterative testing & code refinements. |  | Not Started
Week 7 | 26 Oct - 01 Nov | Developing (UI Integration) | Integrate user interface with backend logic. Handle basic form validation & operational errors. |  | Not Started
Week 8 | 02 Nov - 08 Nov | Developing (Advanced Features) | Implement complex features (e.g., analytics, automation, security). Maintain rigorous iterative testing logs. |  | Not Started
Week 9 | 09 Nov - 15 Nov | Developing (Refinement) | Refine code, improve error handling, clean variable naming, and fully populate the technical iterative diary. |  | Not Started
Week 10 | 16 Nov - 22 Nov | Testing (System Test) | Execute the formal system Test Plan using real, erroneous, and boundary data. Gather full screenshot evidence. |  | Not Started
Week 11 | 23 Nov - 29 Nov | Evaluation (User Feedback) | Present solution to the target user. Gather formal feedback via questionnaires/interviews against success criteria. |  | Not Started
Week 12 | 30 Nov - 06 Dec | Evaluation (Write-up) | Evaluate final product against original criteria. Discuss maintenance opportunities & complete development review. |  | Not Started
Week 13 | 07 Dec - 13 Dec | Final Assembly & Formatting | Compile write-up sections (Analysis to Evaluation), generate code appendices, cross-reference mark scheme. |  | Not Started
Week 14 | 14 Dec - 17 Dec* | FINAL SUBMISSION | 🚨 FINAL SUBMISSION DEADLINE: Thursday 17th December. Clean up files and submit final report. |  | Not Started